## Results Framework
Project Results Framework
Project Title: Emergency and Resilience Response for war-affected communities in Ukraine
Project start date: 01.03.2025
Project duration: 24 months
| Description | Indicator | Target | Implementing Organisation | Location | Means of Verification | Frequencey of measurement
Strategic Objective | To provide crisis-affected communities in Ukraine with life-saving multi-sectoral emergency support, while enabling the sustainable restoration and strengthening of basic services and resilience-building | # women, girls, men and boys reached with life-saving and recovery assistance, disaggregated by gender, age, and vulnerability status | 82612 | ALL | All programme locations | SitReps, Interim and Final Reports | Quarterly
|  | % of women and men that participated in the programme activities and believe that the programme had a positive impact in their lives | 90% | ALL | All programme locations | External Evaluation | One off at the end of programme
|  | % of women and men that participated in the programmereporting that humanitarian assistance is delivered in a safe, accessible, accountable and participatory manner | 90% | ALL | All programme locations | External Evaluation | One off at the end of programme
|  | % of women and men that participated in the programme activities and are satisfied with the aid provided | 90% | ALL | All programme locations | External Evaluation | One off at the end of programme
Outcome 1 | Crisis-affected communities in Ukraine have access to principled, multi-sectoral life-saving assistance to the most vulnerable internally displaced people and non-displaced people affected by the war, ensuring their safety and dignity, especially in areas experiencing high severity levels of need | % of assisted individuals reporting that the support received wasappropriate, and met their priority needs. | 80% | ALL | All programme locations | External Evaluation | One off at the end of programme
|  | % of children showing improved psychosocial wellbeing (baseline/endline) | 30% | LWF | Kharkiv | Endline survey | LWF will do itself
|  | Increased teacher confidence in delivering PSS | 30% | LWF | Kharkiv | Endline survey | LWF will do itself
Output 1.1 | Ensure immediate access to life-saving emergency food assistance for food-insecure people | # of individuals supported through emergency food assistance | 12000 | CWS, HIA, Diakonia CRD | Zakarpattia, Mykolaiv, Dnipropetrovsk, Chernivtsi, Poltava, Odesa | SitReps, Interim and Final Reports | Quarterly
|  | #of individuals receiving emergency food assistance in Poltava | 1000 | Diakonia CRD | Poltava | Activity reports | Quarterly
|  | # of individuals who received food donations | 7500 | CWS | Odesa | Distiribution Lists | Quarterly
Output 1.2 | Provide life-saving emergency shelter and non-food item (NFI) support to internally displaced and non-displaced war-affected people, ensuring their safety and dignity with a focus on areas with high severity level | #of people assisted with NFI support | 11500 | CWS, HIA | Zakarpattia, Mykolaiv, Dnipropetrovsk, Chernivtsi, Odesa | SitReps, Interim and Final Reports | Quarterly
|  | # of people assisted with shelter and NFI in-kind support | 1000 | HIA | Zakarpattia, Mykolaiv, Dnipropetrovsk, Chernivtsi | Handover documents, PDM, work progress reports, field monitoring reports, MoUs | Quarterly
|  | Number of individuals supported with essential NFIs | 7500 | CWS | Odesa | Distiribution Lists | Quarterly
Output 1.3 | Ensure access to adequate housing and common services for internally displaced and non-displaced war-affected people, ensuring their protection, safety and dignity and fostering linkages to longer-term solutions | #of housing unites repaired and made safe | 1350 | HEKS/EPER, LWF | Kharkhiv | SitReps, Interim and Final Reports | Quarterly
|  | # of apartments repaired and improved | 900 | LWF | Kharkhiv | Activity report | Monthly
|  | # of houses repaired through ligh and medium repairs scheme | 450 | HEKS/EPER | Kharkhiv | BoQ, database
Output 1.4 | Deliver life-saving emergency shelter and NFI assistance, mitigating the impacts of harsh winter weather for internally displaced and non-displaced war-affected people, ensuring their safety and dignity with a focus on areas with high severity levels | # of individuals supported to withstand winter weather adversities | 6455 | HIA, CWS, LWF | Kharkhiv, Sumy | SitReps, Interim and Final Reports | Quarterly
|  | # of people with assisted with winter heating | 1000 | HIA | Zakarpattia, Mykolaiv, Dnipropetrovsk | Handover documents, PDM | PDM: 4-6 weeks after distribution
|  | # of people with assisted with winter heating | 1400 | CWS | Odesa | Distiribution Lists | Quarterly
|  | # of households benefiting from emergency NFI and winterization items | 300 | LWF | Kharkhiv, Sumy | Activity report, PDM | Monthly
Output 1.5 | The most vulnerable internally displaced and non-displaced war-affected girls and boys have timely access to well-coordinated and quality child protection services | # of girls and boys with access to child protection services | 1678 | CWS, Diakonia CRD | Poltava, Kharkiv | SitReps, Interim and Final Reports | Quarterly
|  | # of children participating in various support activites | 1603 | Diakonia CRD | Poltava, Kharkiv | Activity Report | Quarterly
|  | #of children accessing child friendly spaces | 75 | CWS | Odesa | Sign-in Sheets | Quarterly
Output 1.6 | Ensure vulnerable internally displaced and non-displaced war-affected people at heightened risk are provided with principled and inclusive protection assistance and services | # of women, girls,boys and men accessing protection services | 12082 | CWS, Diakonia CR, HEKS/EPER, HIA, LWF, ELEOS | Kharkhiv, Odesa, Poltava | SitReps, Interim and Final Reports | Quarterly
|  | # of participants in community psychosocial group activities | 45 | CWS | Odesa | Project Records; Sign-in Sheets | Quarterly
|  | # of individuals receiving focused psychosocial support | 60 | CWS | Odesa | Sign-in Sheets | Quarterly
|  | # of consultations provided for mental health & psychosocial support | 613 | CWS | Odesa | Project Records; Distribution Lists | Quarterly
|  | # of individuals receiving individual legal assistance support | 108 | CWS | Odesa | Project Records | Quarterly
|  | # of children reached with MHPSS activities | 4500 | LWF | Kharkhiv, | Activity report | Monthly
|  | # of PSS session conducted for children | 150 | LWF | Kharkiv | Actiivty Report | Monthly
|  | Increased caregiver awareness of inclusive education and PSS | 30% | LWF | Kharkiv | Actiivty Report | Monthly
|  | # of people provided with legal conseling | 0 | LWF | Kharkhiv | Activity report | Monthly
|  | # of participants receiving protection services, disaggregated by type of service (case management, training) | 2335 | HEKS/EPER | Kharkiv, Odesa | Registration lists, database | Quarterly
|  | # of individuals participating in sessions of psychosocial support | 486 | Diakonia CRD | Poltava, Kharkiv | Activity Report | Quarterly
|  | # of people received protection assistance | 2500 | HIA | Lviv, Ivano-Frankivsk, Kyiv, Zakarpattia, Mykolaiv, Dnipropetrovsk, | Attendance sheets, Surveys for targeted people, KIIs, monitoring reports | Surveys after completion of activity (e.g. training, camp, project etc.)
|  | # of individuals who received cash assistance for protection | 100 | HEKS/EPER | Kharkiv, Odesa | Database | Quarterly
|  | # of teachers trained on PSS, PFA and classroom based PSS including self-care | 460 | LWF | Kharkhiv | Activity report | Quarterly
|  | % able to apply PSS skills | 90% | LWF | Kharkhiv | Activity report | Quarterly
|  | # of people including parents provided with MHPSS support including parenting skills | 1500 | LWF | Kharkhiv, sumy | Activity report | Quarterly
|  | # of participants in community psychosocial group activities | 80 | ELEOS | Sumy | Project Records; Sign-in Sheets | Monthly
|  | # of consultations provided for mental health & psychosocial support | 840 | ELEOS | Sumy | Project Records; Sign-in Sheets | Monthly
|  | # of individuals receiving individual legal assistance support | 105 | ELEOS | Sumy | Project Records; Sign-in Sheets | Monthly
|  | # of people received protection assistance | 263 | ELEOS | Sumy | Project Records; Sign-in Sheets | Monthly
Output 1.7 | Provide life-saving essential health services for the most vulnerable people and communities affected by the war | Number of people supported in accessing health care services | 750 | CWS | Odesa | Projects Records; Distribution Lists | Quarterly
Output 1.8 | Restoring essential WASH services (water systems) in underserved, conflict-affected communities | Number of people with access to safe water | 3000 | HEKS/EPER, | Kharkivska | Activity report | Quarterly
Outcome 2 | Crisis-affected communities in Ukraine have access to essential services for the most vulnerable internally displaced and non-displaced people affected by the war, in areas experiencing high severity levels of need, ensuring protection, safety and dignity | % of crisis-affected individuals in high-severity areas who report that essential services were available, accessible, and met their priority need | 80% | CWS, HIA, HEKS/EPER, LWF | Kharkhiv | External Evaluation | One off at the end of programme
|  | % of schools with safe, and inclusive in-person learning environments | 100% | LWF | Kharkiv | Endline survey | LWF will do itself
|  | % of students reporting feeling safe at school | 90% | LWF | Kharkiv | Endline survey | LWF will do itself
|  | % increase in school attendance among targeted children | 10% | LWF | Kharkiv | Endline survey | LWF will do itself
Output 2.1 | Provide multipurpose cash support to conflict-affected vulnerable households addressing basic needs | # of women, girls, boys and men who received multipurpose cash grants | 2721 | CWS, HIA, HEKS/EPER, LWF | Kharkhiv | SitReps, Interim and Final Reports | Quarterly
|  | # of individuals who received multipurpose cash grant | 590 | LWF | Kharkhiv, Sumy | Distibution list , PDM | Quarterly
|  | #of individuals who received multipurpose cash grant | 1000 | HEKS/EPER | Odesa | Database
|  | # of individals supported with cash asstiance adressing their basic needs | 431 | HIA | Lviv, Ivano-Frankivsk, Kyiv, Zakarpattia, Mykolaiv, Dnipropetrovsk, | Financial records, project progress reports, PDM | PDM: 4-6 weeks after cash payment
|  | # of individuals who received multipurpose cash grant | 350 | CWS | Odesa | Distribution Lists | Quarterly
|  | # of individuals who received multipurpose cash grant | 350 | ELEOS | Konotop (Sumy), Zvyagel (Zhytomir) | Distribution Lists | PDM: 4-6 weeks after cash payment
Output 2.2 | Protect and restore the essential livelihoods of war-affected people and support off-farm and on-farm livelihoods for vulnerable households to prevent the adoption of negative coping strategies | #of women and men supported to sustain their livelihoods | 2405 | CWS, HIA, LWF | Kharkhiv, Sumy | SitReps, Interim and Final Reports | Quarterly
|  | # of persons who participate in Cash for Work | 100 | CWS | Odesa | Project records | Midterm, Final
|  | # of persons who complete upskilling/retraining | 50 | CWS | Odesa | Project records | Midterm, Final
|  | # of people participated in employment promotion | 25 | HIA | Zakarpattia | Attendance sheets, Surveys for targeted people, KIIs | Surveys after completion of activity (e.g. training)
|  | #of persons who participate in business training and small business grants program | 400 | CWS | Odesa | Project records | Midterm, Final
Output 2.3 | Ensure the most vulnerable people affected or displaced by the war can access basic WASH services and supplies to maintain basic hygienic practices, with a focus on people with disabilities and older people, women and girls | # of women, girls, boys and men with restored access to WASH services and supplies | 3000 | HIA, LWF | Kharkhiv, Sumy | SitReps, Interim and Final Reports | Quarterly
|  | Number of people who benefited with hygiene items | 1000 | LWF | Kharkiv, Sumy | Activity report, PDM | Quarterly
|  | # of people with increased access to basic WASH services and supplies | 2000 | HIA | Mykolaiv, Zakarpattia, Dnipropetrovsk | Handover documents, PDM, work progress reports, field monitoring reports, MoUs | Field monitorings as per workplan, KIIs with authority/customer, PDM: 4-6 weeks after distribution
Output 2.4 | Enable access to life-saving assistance for the most vulnerable internally displaced and non-displaced war-affected people through GBV interventions targeting GBV risk prevention, mitigation and ability of humanitarian actors to ensure their protection, safety and dignity | # of women and men with access to GBV prevention and mitigation activities | 5000 | HEKS/EPER | Kharkiv, Odesa | SitReps, Interim and Final Reports | Quarterly
|  | # of individuals who reached by GBV prevention and empowerment activities | 4000 | HEKS/EPER | Kharkiv, Odesa | Registration lists | Quarterly
|  | # of individuals receiving dignity kits | 1000 | HEKS/EPER | Kharkiv, Odesa | Database | Quarterly
Output 2.5 | Children have improved access to safe, inclusive, and quality education services, ensuring continuity of learning during the crisis | #of girls and boys with access to quality education services | 8128 | DIakonia CRD, LWF | Kharkiv, Sumy, Poltava | SitReps, Interim and Final Reports | Quarterly
|  | # of schools that were renovated/rehabilitated/refurbished/equiped | 13 | LWF | Kharkiv | Activity report | Quarterly
|  | # of children receiving learning material | 1250 | LWF | Kharkiv | Procurement report, distribution lists | Upon finalization of the activity
|  | # of children benefiting from classroom equipment | 4500 | LWF | Kharkiv | Procurement report, distribution lists | Upon finalization of the activity
|  | #of children participating in educational activities | 2378 | Diakonia CRD | Kharkiv, Poltava | Activity Reports | Quarterly
Output 2.7 | Conflict-affected health infrastructure is repaired and restored | # of patients and ppl benefitting from repaired and restored health infrustructure | 1635 | LWF, ELEOS, HIA | Kharkhiv, Sumy | SitReps, Interim and Final Reports | Quarterly
|  | # of patients of the repaired cardiological hospital in Kharkiv | 935 | LWF | Kharkiv | SitReps, Interim and Final Reports | Quarterly
|  | # of medical institutions that received the necessary medical equipment | 3 | ELEOS | Sumy | Database | Monthly
|  | # of patients of the repaired 3 hospital in Sumy | 500 | ELEOS | Sumy | Registration lists | Monthly
|  | # of ppl benefitting from the repair and/or refurbishment of a medical college in Kyiv | 200 | HIA | Kyiv | Project documents | Monthly
Outcome 3 | Crisis-affected communities in Ukraine actively lead and participate in their own recovery, ensuring humanitarian assistance is relevant, inclusive, and accountable to their needs, priorities, and capacities | % of community representatives or local leaders who report increased capacity to engage in humanitarian decision-making and recovery planning | 80% | HEKS/EPER, LWF | Kharkiv, Sumy | External Evaluation | One off at the end of programme
|  | % of crisis-affected individuals who are aware of available feedback and accountability mechanisms and know how to use them | 90% | ALL | Kharkhiv, Sumy | External Evaluation | One off at the end of programme
Output 3.1 | Crisis-affected communities in Ukraine actively lead and participate in their own recovery, ensuring humanitarian assistance is relevant, inclusive, and accountable to their needs, priorities, and capacities | #of community members reached by sclr initiatives | 20725 | HEKS/EPER, LWF | Kharkhiv, Sumy | SitReps, Interim and Final Reports | Quarterly
|  | #of community grants provided | 204 | HEKS/EPER, LWF | Kharkhiv, Sumy | SitReps, Interim and Final Reports | Quarterly
|  | # of grants provided for community led actions | 4 | LWF | Kharkhiv, Sumy | Activty report | Quarterly
|  | # of community members participating in community led actions | 500 | LWF | Kharkhiv, Sumy | Activty report | Quarterly
|  | # of community cash grants distributed | 200 | HEKS/EPER | Western Ukraine | Contracts with communities | Quarterly
|  | #of community members reached by sclr initiatives | 20000 | HEKS/EPER | Western Ukraine | Registration lists, database | Quarterly
|  | # of people participated in community-based rehabilitation and adaptive sports initiatives | 225 | HIA | Zakarpattia | Project records, Surveys for targeted people, KIIs | Final
Output 3.2 | Local partners and professionals are better equipped to meet the unique needs of the affected communities | #of local progessionals, women and men, participating in capacity enhancement activities | 591 | CWS, LWF | Kharkhiv, Sumy | SitReps, Interim and Final Reports | Quarterly SitReps
|  | # of persons trained on protection principles | 29 | CWS | Odesa | Sign-in Sheets | Midterm, Final
|  | # of professionals provided with training on PSEA | 29 | CWS | Odesa | Sign-in Sheets | Midterm, Final
Output 3.3 | Crisis-affected communities have access to effective, transparent and well-coordinated response | # of feedback mechanism channels installed | 9 | ALL | All programme locations | SitReps, Interim and Final Reports | Quarterly
|  | # joint initiaives with local authorities | 1 | LWF | All locations | Activity report, attendance lists | Quarterly
|  | # information products distributed to the affected population through a variety of mechanisms on humanitarian program planning, functioning and progress | 3000 2870 | HEKS/EPER, HIA | All locations | Distribution lists | Quarterly
|  | % feedback received (including complaints) followed up within 14 days after receiving | 95% | HEKS/EPER | All locations | FCRM Database FAM Database | Quarterly
|  | # partner organizations with an operational complaint and feedback mechanism | 3 2 3 | CWS, HIA LWF | All locations | CWS Checklist FAM Checklist | Quarterly
|  | # community-based complaints\feedback mechanisms established | 3 | HEKS/EPER | All locations | FCRM policy | Quarterly
|  | # international, national, regional and local coordination bodies, authorities and partners in which HIA is participating | 10 | HIA | All locations | MoUs, memberhsips, meeting reports | Quarterly
Note on C78: Vita Nesterenko: I added this line, please consider if it is necessary